## Change Register Q1
CIBB — IT Change Register Q1 2026
CR# | Requested By | System Affected | Change Type | Priority | Submitted | CAB Date | Status | Risk Level | Description
CR-2026-001 | Daniel Lim | Core Banking (T24) | Emergency | Critical | 02-Jan-2026 | 03-Jan-2026 | Closed | High | Patch for CVE-2025-9981 SQL injection vulnerability in T24 OFS layer
CR-2026-002 | Priya Subramaniam | Internet Banking Portal | Standard | High | 05-Jan-2026 | 15-Jan-2026 | Implemented | Medium | TLS 1.3 migration for all public-facing endpoints
CR-2026-003 | Adrian Tan | Treasury Murex | Standard | Medium | 08-Jan-2026 | 22-Jan-2026 | Implemented | Low | Murex MX.3 upgrade from v3.1.40 to v3.1.55
CR-2026-004 | Mei Ling Yap | HR Platform (SAP SuccessFactors) | Normal | Low | 10-Jan-2026 | 29-Jan-2026 | Approved | Low | Annual leave entitlement update for 2026 policy
CR-2026-005 | Daniel Lim | SWIFT gpi Integration | Standard | High | 12-Jan-2026 | 05-Feb-2026 | In Progress | Medium | Implement SWIFT ISO 20022 migration — Phase 2
CR-2026-006 | Sarah Ng | AML Screening Engine (Actimize) | Emergency | Critical | 15-Jan-2026 | 16-Jan-2026 | Closed | High | Hotfix for sanctions list false-positive spike (OFAC update Jan-15)
CR-2026-007 | Priya Subramaniam | Data Warehouse (Snowflake) | Standard | Medium | 18-Jan-2026 | 12-Feb-2026 | Pending CAB | Low | Expand Snowflake cluster; add 4 TB storage tier
CR-2026-008 | Adrian Tan | Loan Origination System | Normal | Medium | 20-Jan-2026 | 19-Feb-2026 | Pending CAB | Medium | Add Islamic financing product type to LOS workflow
CR-2026-009 | Mei Ling Yap | Email Gateway (MS Exchange Online) | Standard | Low | 22-Jan-2026 | 26-Feb-2026 | Approved | Low | Configure DLP policies for customer PII data classification
CR-2026-010 | Daniel Lim | Disaster Recovery | Standard | High | 25-Jan-2026 | 05-Mar-2026 | Submitted | Medium | DR drill — failover test for Core Banking to secondary DC Cyberjaya