# CAMPAIGN BRIEF — WEALTH GOALS 2026

Contoso Investment Bank Berhad | Wealth Management & Retail Banking

Brief Ref: MKT-2026-WG-001 | Date: 3 February 2026

Prepared By: Mei Ling Yap, VP Marketing | Approved By: CMO

## 1. CAMPAIGN OVERVIEW

| Parameter | Detail |
| --- | --- |
| Campaign Name | Wealth Goals 2026 |
| Campaign Period | 1 March 2026 — 31 May 2026 (13 weeks) |
| Target Segment | Mass Affluent (investable assets RM 250K–RM 2M); CIBB Priority Banking clients |
| Primary Objective | Increase Wealth AUM by RM 800 million in Q1/Q2 2026 |
| Secondary Objective | Activate 2,500 new Priority Banking customers; cross-sell 1 additional product per active customer |
| Budget | RM 4.2 million (Digital 50%, OOH 20%, Branch 15%, Events 15%) |
| KPIs | AUM growth +RM 800M ¦ New Priority customers: 2,500 ¦ Lead gen: 12,000 qualified leads ¦ ROAS: 4.8x |

## 2. KEY MESSAGES

'Your financial goals deserve a partner who understands Malaysia.' — headline

Feature CIBB's award-winning Wealth Management team (Best Private Bank Malaysia 2025 — The Asset)

Promote bundled Wealth Goals Package: Fixed Deposit + Unit Trust + Takaful + Priority Card

Highlight digital convenience: Wealth Goals tracker in CIBB Mobile App (new feature launch Feb 2026)

Inclusion of Shariah-compliant options prominently — Wealth Goals-i package

## 3. CHANNEL STRATEGY

| Channel | Budget (RM) | Tactic | Target Metric |
| --- | --- | --- | --- |
| Digital — Social | 820,000 | LinkedIn, Meta, TikTok ads; retargeting | CPL < RM 68; 8,000 leads |
| Digital — SEM | 620,000 | Google Search + Display; branded & generic terms | CPL < RM 75; 2,500 leads |
| Digital — Email/SMS | 180,000 | CRM segmented campaigns to 280,000 prospects | Open rate >22%; CTR >4% |
| Out-of-Home | 840,000 | MRT Rapid KL wrap, KLIA digital screens, highway billboards | Impressions 12M+ |
| Branch Activation | 630,000 | POS materials, banker talking points, branch events | 8 flagship branch events |
| Events | 1,110,000 | Wealth Goals Showcase (KL, Penang, JB); exclusive client dinners | 400 HNW attendees |

## 4. PRODUCT HIGHLIGHTS

| Product | Promotional Rate / Offer | Eligibility |
| --- | --- | --- |
| Contoso GOAL Fixed Deposit | 4.25% p.a. (12 months, min RM 50,000) | New & existing CIBB customers |
| CIBB Wealth Unit Trust | 0% sales charge (March–May 2026 promo) | Minimum RM 10,000 new investment |
| Contoso Takaful Wealth Protector | First year premium rebate 15% | New policies incepted during campaign |
| Wealth Goals-i (Islamic) | Profit rate equivalent 4.10% p.a. | Shariah-compliant investors |
| Priority Banking Upgrade | Waived annual fee year 1 (save RM 800) | New Priority Banking activation |

## 5. GOVERNANCE & COMPLIANCE

All campaign materials must be reviewed and approved by Compliance & Legal before publication. Key requirements: SC CMS Act advertising guidelines, BNM Fair Dealing Principles (FDP) compliance, PDPA consent for all digital lead capture, and Shariah Committee endorsement for Wealth Goals-i product materials.

## 6. TIMELINE

| Milestone | Date | Owner |
| --- | --- | --- |
| Campaign brief approved | 3-Feb-2026 | CMO |
| Creative concepts signed off | 17-Feb-2026 | Mei Ling Yap |
| Compliance & Legal clearance | 24-Feb-2026 | Compliance |
| Digital assets finalised | 26-Feb-2026 | Agency — Pixel & Co |
| Campaign LIVE — all channels | 1-Mar-2026 | Marketing Ops |
| Mid-campaign performance review | 1-Apr-2026 | Mei Ling Yap |
| Campaign wrap & post-analysis | 15-Jun-2026 | Mei Ling Yap |